## 0_Instructions
GDC Application Ingestion Template (JFrog-backed Self-Service)
Purpose: capture everything the platform team needs to ingest an application's artifacts into JFrog and generate the deployment pipeline (K8s / VM / Terraform) onto GDC.
How to fill in
1. Start with 1_App_Overview (one per application).
2. List every deployable piece in 2_Components (K8s workloads, VMs, Terraform stacks, day-2 config).
3. List EVERY artifact that must exist in JFrog in 3_Artifact_Inventory, including transitive ones (e.g. images referenced inside a Helm chart, init/sidecar images, OS packages, Terraform providers, Ansible collections).
4. Complete 4_K8s_Deployment for each K8s component and 5_VM_Deployment for each VM component.
5. Complete 6_Terraform for every Terraform stack (infra provisioning AND day-2 config such as GitLab/Jira projects, groups).
6. Complete 7_Network_Flows, 8_Secrets_Config, 9_Deploy_Sequence and 10_Readiness_Checklist.
Conventions
- Columns/attributes marked * or Required=Yes are mandatory for ingestion approval.
- Yellow cells are the worked EXAMPLE (Jira Software Data Center). Replace or append your own rows.
- Values marked 'confirm' are illustrative and must be verified against vendor docs / platform standards.
- Never put secret VALUES in this workbook; reference the secret store path only.
- Pin every artifact to an exact version, and to a digest/checksum where possible (no 'latest').
- Use dropdowns where provided; lists are maintained in the Lookups sheet.
Example scenario: Jira
Jira Software DC runs on GDC K8s using the vendor (Atlassian) Helm chart. GDC has no managed PostgreSQL 17, so PostgreSQL 17 is deployed on a GDC VM, provisioned by Terraform and configured by Ansible using Debian packages proxied through JFrog. Jira projects/groups are created day-2 via a Terraform provider.

## 1_App_Overview
Attribute | Description / Guidance | Required | Value (Example: Jira)
Identification
Ingestion Request ID | Unique ID (e.g. Jira ticket key of the request) | Yes | ING-2026-001
Application Name | Full product name | Yes | Jira Software Data Center
Application Short Code | Lowercase, used for namespaces, repo keys, DNS | Yes | jira
Business Description | What the app does / who uses it | Yes | Issue and project tracking for engineering teams
Application Type | COTS / OSS / In-house | Yes | COTS (Vendor)
Vendor / Upstream Source | Vendor or project name | Yes | Atlassian
Application Version | Exact product version to ingest | Yes | 10.3.x LTS (example - confirm exact patch)
Vendor Documentation URL | Install / Helm / support matrix docs | Yes | https://atlassian.github.io/data-center-helm-charts/
Deployment Pattern | K8s only / VM only / Hybrid | Yes | Hybrid: K8s (Helm) + VM (PostgreSQL) + Terraform
Ownership & Support
Business Owner | Name / email | Yes | <name@org>
Technical Owner | Name / email | Yes | <name@org>
Support Team / On-call | Team / rotation / escalation | Yes | Collaboration Tools Team
Requesting Team GitLab Group | Where app config/IaC repos live | Yes | gitlab/collab-tools/jira
Cost Center |  | No | <cost-center>
Vendor Support Contract | Contract ID / expiry | No | <contract-id>
Classification & Compliance
Data Classification | Public / Internal / Confidential / Restricted | Yes | Confidential
Criticality Tier | Drives HA / DR / change process | Yes | Tier 1 - Business Critical
Compliance Requirements | e.g. FedRAMP, ISO 27001, CIS, STIG | Yes | CIS hardened OS, audit logging enabled
License Type | Commercial / OSS licence (Apache-2.0, GPL ...) | Yes | Commercial (Atlassian DC subscription)
License Key Handling | Where licence key is stored | Yes | Vault: secret/apps/jira/license
Target Environment
Target Environments | Dev / Test / Stage / Prod | Yes | Dev, Test, Prod
GDC Organization / Project | GDC org & project identifiers | Yes | org-collab / prj-jira
GDC Zone(s) | Zones for deployment | Yes | zone-1 (Prod: zone-1 + zone-2)
K8s Cluster(s) | User cluster name(s) | Yes | user-cluster-apps-01
Air-gapped? | Is upstream internet reachable only via JFrog? | Yes | Yes - all artifacts via JFrog only
Expected Users / Load | Concurrent users, growth | Yes | 2,000 named / 400 concurrent
HA Requirement | Replicas, multi-zone | Yes | Jira 2+ pods (DC clustering), PG primary + standby
RTO / RPO |  | Yes | RTO 4h / RPO 15m
Target Go-Live Date |  | No | 2026-12-15

## 2_Components
Component ID * | Component Name * | Description * | Deployment Target * | Provided By * | Depends On (Component IDs) | Environments * | Why this target? (justification) | Owner * | Notes
C01 | Jira Software DC | Jira application pods (StatefulSet) | K8s - Helm Chart | Vendor | C02, C04, C05, C07 | Dev, Test, Prod | Vendor ships official Helm chart | Collab Tools Team | Chart: atlassian-data-center/jira
C02 | PostgreSQL 17 database | Jira backend database | VM - Ansible | Open Source Community | C03 | Dev, Test, Prod | GDC has no managed PostgreSQL 17 service | Platform DBA | Packages from apt.postgresql.org via JFrog Debian remote
C03 | PostgreSQL VM infrastructure | VM(s), disks, network for PostgreSQL | Terraform - Infra Provisioning | Platform Team |  | Dev, Test, Prod | Standard platform VM module | Platform Team | Primary + standby in Prod
C04 | Jira K8s namespace baseline | Namespace, quotas, limit ranges, network policies, imagePullSecret | Terraform - Infra Provisioning | Platform Team |  | Dev, Test, Prod | Self-service namespace onboarding | Platform Team
C05 | Jira shared home storage | RWX volume for Jira DC shared home | Platform Shared Service | Platform Team | C04 | Dev, Test, Prod | Required by Jira DC clustering | Platform Team | RWX StorageClass (NFS/file) - confirm availability on GDC
C06 | Jira day-2 configuration | Projects, groups, memberships, permission schemes | Terraform - Day-2 Configuration | App Team | C01 | Dev, Test, Prod | Config-as-code instead of manual admin | Collab Tools Team | Uses Jira Terraform provider (community - security review)
C07 | Jira ingress & TLS | Ingress host, TLS certificate | Platform Shared Service | Platform Team | C04 | Dev, Test, Prod | Standard ingress | Platform Team | Cert from internal CA / cert-manager
C08 | GitLab project for Jira IaC | GitLab group/project holding Jira Helm values & Terraform | Terraform - Day-2 Configuration | Platform Team |  | All | Self-service repo bootstrap | Platform Team | gitlabhq/gitlab provider

## 3_Artifact_Inventory
Artifact ID * | Component ID * | Artifact Type * | Artifact Name * | Version / Tag * | Upstream Source (registry / URL) * | Full Upstream Reference * | Digest / SHA256 Checksum * | Signature / Provenance Available | SBOM Available | License * | JFrog Package Type * | JFrog Repo Type * | Target JFrog Repo Key * | Ingestion Method * | Reference After Ingestion (JFrog path) * | Xray Scan Required * | Referenced By (transitive) | Optional? | Notes
A01 | C01 | Helm Chart | jira | 1.x (example - confirm) | https://atlassian.github.io/data-center-helm-charts | atlassian-data-center/jira | <sha256 of .tgz> | No | No | Apache-2.0 | helm | Remote | helm-remote-atlassian -> helm-virtual | Remote repo proxy/cache | https://<jfrog>/artifactory/api/helm/helm-virtual (chart: jira) | Yes |  | No | Override image.repository to JFrog docker-virtual in values
A02 | C01 | Docker/OCI Image | atlassian/jira-software | 10.3.x (example - confirm) | docker.io | docker.io/atlassian/jira-software:<tag> | sha256:<digest> | TBD | TBD | Commercial | docker | Remote | docker-remote-dockerhub -> docker-virtual | Pull-Scan-Push to Local | <jfrog>/docker-virtual/atlassian/jira-software:<tag> | Yes | A01 (image.repository) | No | Pin by digest in values
A03 | C01 | Docker/OCI Image | alpine (nfs permission fixer init container) | <pinned tag> | docker.io | docker.io/library/alpine:<tag> | sha256:<digest> | No | No | MIT | docker | Remote | docker-remote-dockerhub -> docker-virtual | Pull-Scan-Push to Local | <jfrog>/docker-virtual/library/alpine:<tag> | Yes | A01 (volumes.sharedHome.nfsPermissionFixer) | Yes | Confirm via 'helm template' whether enabled
A04 | C01 | Docker/OCI Image | fluentd sidecar | <pinned tag> | docker.io | <per chart values: fluentd.imageRepo> | sha256:<digest> | No | No | Apache-2.0 | docker | Remote | docker-remote-dockerhub -> docker-virtual | Pull-Scan-Push to Local | <jfrog>/docker-virtual/<fluentd-image>:<tag> | Yes | A01 (fluentd.enabled) | Yes | Only if log shipping sidecar enabled
A05 | C02 | Debian Package | postgresql-17, postgresql-client-17, postgresql-common | 17.x (pinned minor) | https://apt.postgresql.org/pub/repos/apt | deb <dist>-pgdg main | Repo Release/InRelease signed | Yes (GPG signed repo) | No | PostgreSQL License | debian | Remote | debian-remote-pgdg -> debian-virtual | Remote repo proxy/cache | https://<jfrog>/artifactory/debian-virtual <dist>-pgdg main | Yes |  | No | See docs/jfrog-debian-repository.md
A06 | C02 | GPG Key / Certificate | PGDG repository signing key | current | https://www.postgresql.org/media/keys/ACCC4CF8.asc | ACCC4CF8.asc | <sha256> | N/A | N/A | N/A | generic | Local | generic-local/keys/pgdg/ | Manual upload (vendor portal) | <jfrog>/generic-local/keys/pgdg/ACCC4CF8.asc | No | A05 | No | Needed by apt on air-gapped VM
A07 | C02 | Ansible Role | postgresql (internal) | v1.0.0 | Internal GitLab | roles/postgresql (this repo) | <git tag commit sha> | N/A | N/A | Internal | generic | Local | ansible-local | Built internally (CI publish) | <jfrog>/ansible-local/roles/postgresql-1.0.0.tar.gz | No |  | No | Playbook: playbooks/postgresql.yml
A08 | C02 | Ansible Collection | community.postgresql | <pinned version> | https://galaxy.ansible.com | community.postgresql:<version> | <sha256> | No | No | GPL-3.0 | ansible | Remote | ansible-remote-galaxy -> ansible-virtual | Remote repo proxy/cache | <jfrog>/api/ansible/ansible-virtual | Yes | A07 | No | Used for DB/user creation
A09 | C02 | VM / OS Image | Ubuntu 22.04 LTS (CIS hardened) | <image version> | GDC VM image catalog | <gdc image name> | <sha256> | TBD | TBD | Canonical | generic | Local | vm-images-local | Built internally (CI publish) | <jfrog>/vm-images-local/ubuntu-22.04-cis/<ver> | Yes |  | No | Platform golden image - confirm PG17 dist support
A10 | C03, C04 | Terraform Provider | hashicorp/kubernetes | <pinned version> | registry.terraform.io | hashicorp/kubernetes | <sha256 (lock file)> | Yes (HashiCorp signed) | No | MPL-2.0 | terraform | Remote | terraform-remote-hashicorp -> terraform-virtual | Remote repo proxy/cache | <jfrog>/terraform-virtual (provider mirror) | Yes |  | No | GDC VMs/namespaces via KRM API - confirm provider choice with platform
A11 | C03 | Terraform Module | gdc-vm (platform module) | v2.x | Internal GitLab | platform/terraform-modules/gdc-vm | <git tag> | N/A | N/A | Internal | terraform | Local | terraform-modules-local | Built internally (CI publish) | <jfrog>/terraform-modules-local/platform/gdc-vm/<ver> | No |  | No
A12 | C06 | Terraform Provider | Jira provider (e.g. fourplusone/jira) | <pinned version> | registry.terraform.io | fourplusone/jira (community - confirm) | <sha256 (lock file)> | TBD | No | MPL-2.0 (confirm) | terraform | Remote | terraform-remote-hashicorp -> terraform-virtual | Pull-Scan-Push to Local | <jfrog>/terraform-virtual (provider mirror) | Yes |  | No | Community provider - security & compatibility review with Jira 10
A13 | C08 | Terraform Provider | gitlabhq/gitlab | <pinned version> | registry.terraform.io | gitlabhq/gitlab | <sha256 (lock file)> | Yes | No | MPL-2.0 | terraform | Remote | terraform-remote-hashicorp -> terraform-virtual | Remote repo proxy/cache | <jfrog>/terraform-virtual (provider mirror) | Yes |  | No | GitLab groups/projects for Jira IaC

## 4_K8s_Deployment
Attribute | Description / Guidance | Required | C01 - Jira (Example) | <Next K8s component>
Packaging
Component ID | From 2_Components | Yes | C01
Packaging Type | Helm chart / raw manifests / Kustomize | Yes | Helm chart (vendor)
Chart Name & Version | Exact chart version | Yes | atlassian-data-center/jira 1.x (confirm)
Chart Source in JFrog | Virtual repo URL | Yes | helm-virtual
Values File Location | GitLab path per environment | Yes | gitlab/collab-tools/jira/helm/values-<env>.yaml
All Images Rendered by Chart | Output of 'helm template ... ¦ grep image:' - every image must be in 3_Artifact_Inventory | Yes | A02, A03 (A04 if fluentd enabled)
Image Registry Override Keys | Values keys used to point images at JFrog | Yes | image.repository, image.tag, fluentd.imageRepo
CRDs / Cluster-scoped Resources | Any CRDs, ClusterRoles, webhooks | Yes | None
Helm Hooks / Jobs | Pre/post install jobs | No | None
Runtime
Namespace |  | Yes | jira-<env>
Workload Kind | Deployment / StatefulSet / DaemonSet | Yes | StatefulSet
Replicas (per env) |  | Yes | Dev 1 / Test 1 / Prod 2+
CPU Request / Limit | Per pod | Yes | 2 / 4 (size per load - confirm)
Memory Request / Limit | Per pod | Yes | 4Gi / 6Gi; JVM heap via jira.resources.jvm.maxHeap
Container Ports |  | Yes | 8080 (http), 40001/40011 (cluster cache)
Service Type | ClusterIP / LoadBalancer | Yes | ClusterIP
Health Probes | Readiness / liveness endpoints | Yes | /status (chart default)
HPA / PDB |  | No | No HPA; PDB minAvailable 1 in Prod
Session Affinity |  | Yes | Sticky sessions required when replicas > 1
Storage
Local Home PVC | Size / StorageClass / access mode | Yes | volumes.localHome: 20Gi, <rwo-class>, RWO
Shared Home PVC | Size / StorageClass / access mode | Yes | volumes.sharedHome: 100Gi, <rwx-class>, RWX
Backup of PVs | Tool / schedule | Yes | Platform backup (e.g. Velero/GDC backup) daily
Security
Pod Security Context | runAsUser / fsGroup / privileged? | Yes | fsGroup 2001, non-root, not privileged
Service Account / RBAC |  | Yes | Chart-created SA, no cluster RBAC
imagePullSecret | JFrog pull token secret name | Yes | jfrog-pull (created by C04)
Network Policies | Ingress/egress allowed | Yes | Allow ingress-nginx -> 8080; egress to PG VM 5432, SMTP, LDAP
Integration
Ingress Host |  | Yes | jira.<env>.gdc.example.org
Ingress Class / TLS |  | Yes | nginx; TLS secret jira-tls (internal CA)
Database Connection | Values keys | Yes | database.type=postgres72; database.url=jdbc:postgresql://pg17-jira-<env>:5432/jiradb; database.driver=org.postgresql.Driver
Database Credentials Secret |  | Yes | database.credentials.secretName=jira-db-credentials
Other External Dependencies | SMTP, LDAP/AD, SSO | No | SMTP relay, AD (LDAPS 636), SAML SSO
Observability | Metrics / logs / dashboards | No | JMX exporter (monitoring.exposeJmxMetrics), stdout to platform logging

## 5_VM_Deployment
Attribute | Description / Guidance | Required | C02 - PostgreSQL 17 (Example) | <Next VM component>
Infrastructure
Component ID | From 2_Components | Yes | C02 (infra by C03)
VM Role |  | Yes | PostgreSQL 17 database server
Reason for VM (not K8s / managed) |  | Yes | GDC has no managed PostgreSQL 17; stateful DB on VM per platform standard
OS Image & Version | Must be in 3_Artifact_Inventory | Yes | Ubuntu 22.04 LTS CIS (A09) - confirm PGDG support
VM Count per Env |  | Yes | Dev 1 / Test 1 / Prod 2 (primary + standby)
vCPU / RAM |  | Yes | 4 vCPU / 16 GiB (Prod 8 / 32)
OS Disk |  | Yes | 50 GiB
Data Disk(s) & Mount |  | Yes | 200 GiB at /var/lib/postgresql (Prod 500 GiB)
Network / Subnet / Static IP |  | Yes | db-subnet; static IP; DNS pg17-jira-<env>
Provisioned By | Terraform stack ID from 6_Terraform | Yes | T01
Configuration (Ansible)
Playbook |  | Yes | playbooks/postgresql.yml
Roles |  | Yes | roles/postgresql (A07)
Collections |  | Yes | community.postgresql (A08)
Inventory Group |  | Yes | postgresql_jira_<env>
Package Repos (JFrog) | apt/yum repo URLs used on the VM | Yes | debian-virtual (<dist>-pgdg main) + key A06
Packages & Versions |  | Yes | postgresql-17, postgresql-client-17 (pinned)
Key Ansible Variables | No secret values | Yes | postgresql_version=17; db=jiradb; owner=jirauser; encoding UNICODE; LC_COLLATE/LC_CTYPE 'C'; template0
Service Ports |  | Yes | 5432/tcp
pg_hba / Allowed Clients |  | Yes | K8s pod/egress CIDR of user-cluster-apps-01, scram-sha-256, TLS required
OS Service Accounts |  | Yes | postgres (system), ansible (automation, sudo)
Hardening Baseline |  | Yes | CIS Level 1 + PostgreSQL CIS benchmark
Operations
Backup Tool / Schedule / Retention |  | Yes | pgBackRest: full weekly, diff daily, WAL archive; 30-day retention
HA / Replication |  | Yes | Streaming replication to standby (Prod)
Monitoring |  | Yes | postgres_exporter + node_exporter to platform Prometheus
Patching Window |  | Yes | Monthly, Sun 02:00-04:00
Upgrade Path |  | No | Minor via apt pin bump; major via pg_upgrade runbook
Decommission Playbook |  | No | playbooks/postgresql-uninstall.yml

## 6_Terraform
Stack ID * | Component ID * | Purpose * | Description * | Code Location (GitLab repo/path) * | Terraform Version * | Providers (source@version) * | Provider Artifact IDs * | Modules (source@version) | State Backend * | Auth / Credentials Method * | Resources Managed * | Run By (pipeline / stage) * | Approval Gate * | Drift Detection | Environments * | Notes
T01 | C03 | Infra Provisioning | PostgreSQL VM(s), disks, DNS | gitlab/collab-tools/jira/terraform/infra-vm | >= 1.6 (pinned) | hashicorp/kubernetes@<ver> | A10 | platform/gdc-vm@v2.x (A11) | GitLab-managed TF state (http backend) | GDC service account token from Vault | VirtualMachine, VirtualMachineDisk, DNS record | Ingestion pipeline: provision-infra | Plan review by Platform | Nightly plan | Dev, Test, Prod | Confirm GDC VM API/provider with platform
T02 | C04 | Infra Provisioning | Namespace baseline for Jira | gitlab/platform/namespaces/jira | >= 1.6 (pinned) | hashicorp/kubernetes@<ver> | A10 | platform/namespace-baseline@v1.x | GitLab-managed TF state | Platform SA (Vault) | Namespace, ResourceQuota, LimitRange, NetworkPolicy, imagePullSecret | Ingestion pipeline: provision-infra | Auto (policy-checked) | Nightly plan | Dev, Test, Prod
T03 | C06 | Day-2 Configuration | Jira projects, groups, memberships | gitlab/collab-tools/jira/terraform/day2-config | >= 1.6 (pinned) | fourplusone/jira@<ver> (confirm) | A12 |  | GitLab-managed TF state | Jira admin API token from Vault | jira_project, jira_group, jira_group_membership (confirm resources) | App pipeline: configure | App owner approval | Weekly plan | Dev, Test, Prod | Runs after Jira is healthy (step 8)
T04 | C08 | Platform Bootstrap | GitLab group/project for Jira IaC | gitlab/platform/gitlab-config | >= 1.6 (pinned) | gitlabhq/gitlab@<ver> | A13 |  | GitLab-managed TF state | GitLab group access token from Vault | gitlab_group, gitlab_project, gitlab_group_membership, protected branches | Onboarding pipeline | Platform approval | Weekly plan | All | Runs once at onboarding

## 7_Network_Flows
Flow ID * | Source * | Destination * | Port(s) * | Protocol * | Direction * | Purpose * | Encrypted (TLS)? * | Environments * | Notes
N01 | End users (corp network) | Ingress jira.<env>.gdc.example.org | 443 | TCP | Inbound | Jira UI/API | Yes | All
N02 | Ingress controller | Jira pods | 8080 | TCP | Internal (east-west) | App traffic | No (in-cluster) | All
N03 | Jira pods | Jira pods | 40001, 40011 | TCP | Internal (east-west) | DC cluster cache replication | No | Prod | Only when replicas > 1
N04 | Jira pods (cluster egress) | PostgreSQL VM | 5432 | TCP | Outbound | Database | Yes | All
N05 | Jira pods | SMTP relay | 587 | TCP | Outbound | Email notifications | Yes | All
N06 | Jira pods | AD / LDAP | 636 | TCP | Outbound | User directory | Yes | All
N07 | K8s nodes | JFrog Artifactory | 443 | TCP | Outbound | Image / chart pulls | Yes | All
N08 | PostgreSQL VM | JFrog Artifactory | 443 | TCP | Outbound | apt packages | Yes | All
N09 | Ansible runner | PostgreSQL VM | 22 | TCP | Inbound | Configuration | Yes | All
N10 | Terraform runner | Jira API | 443 | TCP | Outbound | Day-2 config (T03) | Yes | All
N11 | PostgreSQL primary | PostgreSQL standby | 5432 | TCP | Internal (east-west) | Streaming replication | Yes | Prod
N12 | PostgreSQL VM | Backup storage | 443 | TCP | Outbound | pgBackRest repository | Yes | All

## 8_Secrets_Config
Secret ID * | Secret Name * | Used By (Component) * | Type * | Source of Truth * | Path / Reference (NO VALUES) * | Delivered Via * | Rotation * | Owner * | Notes
S01 | jira-db-credentials | C01, C02 | DB username/password | HashiCorp Vault | secret/apps/jira/<env>/db | ExternalSecrets -> K8s Secret; Ansible lookup | 90 days | Platform DBA
S02 | postgres superuser | C02 | DB password | HashiCorp Vault | secret/platform/pg/jira-<env>/postgres | Ansible lookup | 90 days | Platform DBA
S03 | Jira license key | C01 | License | HashiCorp Vault | secret/apps/jira/license | Entered at setup / K8s Secret | On renewal | Collab Tools Team
S04 | jira-tls | C07 | TLS certificate | Internal CA / cert-manager | ClusterIssuer internal-ca | cert-manager Certificate | Auto (90 days) | Platform Team
S05 | jfrog-pull | C04 | Registry pull token | JFrog Access Token | secret/platform/jfrog/pull/jira | imagePullSecret | 30 days | Platform Team | Read-only, scoped to docker-virtual
S06 | jira-admin-api-token | C06 | API token | HashiCorp Vault | secret/apps/jira/<env>/tf-admin | GitLab CI (Vault JWT auth) | 90 days | Collab Tools Team
S07 | ldap-bind | C01 | Service account | HashiCorp Vault | secret/apps/jira/<env>/ldap | Jira admin UI / K8s Secret | 180 days | Identity Team
S08 | gitlab-group-token | C08 | API token | HashiCorp Vault | secret/platform/gitlab/tf | GitLab CI (Vault JWT auth) | 90 days | Platform Team

## 9_Deploy_Sequence
Step * | Pipeline Stage * | Action * | Component / Stack * | Tool * | Depends On Step * | Success Criteria * | Rollback
1 | ingest | Pull/proxy all artifacts A01-A13 into JFrog, Xray scan, promote to virtual repos | All | JFrog CLI / Xray |  | All artifacts present; no Critical/High CVEs without waiver | Delete from local repo
2 | validate | helm template with JFrog overrides; assert no non-JFrog image refs | C01 | Helm | 1 | 0 images outside <jfrog> registry | N/A
3 | provision-infra | Create namespace baseline | T02 | Terraform | 1 | Namespace + quotas + pull secret exist | terraform destroy (non-prod)
4 | provision-infra | Provision PostgreSQL VM(s) | T01 | Terraform | 1 | VM reachable via SSH from Ansible runner | terraform destroy (non-prod)
5 | configure-vm | Install & configure PostgreSQL 17, create jiradb/jirauser | C02 | Ansible | 4 | psql connect as jirauser from K8s egress succeeds | playbooks/postgresql-uninstall.yml
6 | secrets | Sync secrets S01, S03-S05 into namespace | C04 | ExternalSecrets | 3, 5 | Secrets present in namespace | N/A
7 | deploy-app | helm upgrade --install jira with env values | C01 | Helm | 2, 6 | Pods Ready; /status returns RUNNING | helm rollback
8 | configure-app | Apply Jira projects/groups | T03 | Terraform | 7 | terraform plan shows no drift | terraform apply previous state
9 | verify | Smoke tests: login, create issue, DB connectivity, email | C01 | Test suite | 8 | All smoke tests pass | Rollback steps 7-8

## 10_Readiness_Checklist
# * | Category * | Check * | Owner * | Status * | Evidence / Link | Notes
1 | Vendor Support | Vendor supported-platforms matrix confirms Jira version supports PostgreSQL 17 | Collab Tools Team | Not Started |  | Blocker if unsupported - fall back to supported PG major
2 | Vendor Support | Helm chart version compatible with Jira version and GDC K8s version | Platform Team | Not Started
3 | Artifacts | Every image rendered by 'helm template' is listed in 3_Artifact_Inventory | Platform Team | Not Started
4 | Artifacts | All artifacts pinned by version AND digest/checksum (no 'latest') | App Team | Not Started
5 | Security | Xray scan: no Critical/High CVEs, or approved waivers recorded | Security | Not Started
6 | Security | Licences reviewed and approved (incl. GPL collections, community providers) | Legal / OSPO | Not Started
7 | Security | Community Terraform providers reviewed (source, maintainer, signature) | Security | Not Started |  | A12
8 | Security | No secret values stored in Git, values files or this workbook | App Team | Not Started
9 | Infra | RWX StorageClass available on target GDC cluster | Platform Team | Not Started |  | C05
10 | Infra | Quota (CPU/RAM/storage/IP) available in GDC project | Platform Team | Not Started
11 | Network | All flows in 7_Network_Flows approved and firewall rules raised | Network Team | Not Started
12 | Operations | Backup + restore tested for PostgreSQL and Jira shared home | Platform DBA | Not Started
13 | Operations | Monitoring/alerts and runbooks in place | App Team | Not Started
14 | Approval | Ingestion approved by Platform & Security | Platform Lead | Not Started

## Lookups
YesNo | AppType | DeployTarget | ProvidedBy | ArtifactType | JFrogPkgType | JFrogRepoType | IngestionMethod | Environment | Criticality | DataClass | TFPurpose | SecretStore | Status | Direction
Yes | COTS (Vendor) | K8s - Helm Chart | Vendor | Helm Chart | helm | Remote | Remote repo proxy/cache | Dev | Tier 0 - Mission Critical | Public | Infra Provisioning | HashiCorp Vault | Not Started | Inbound
No | Open Source | K8s - Docker Image (raw manifests) | Open Source Community | Docker/OCI Image | docker | Local | Pull-Scan-Push to Local | Test | Tier 1 - Business Critical | Internal | Day-2 Configuration | K8s Secret (ExternalSecrets) | In Progress | Outbound
N/A | In-house | K8s - Kustomize | Platform Team | Debian Package | oci | Virtual | Manual upload (vendor portal) | Stage | Tier 2 - Important | Confidential | Platform Bootstrap | Ansible Vault | Done | Internal (east-west)
TBD | SaaS Integration | VM - Ansible | App Team | RPM Package | debian | Federated | Built internally (CI publish) | Prod | Tier 3 - Low | Restricted |  | GitLab CI Variable (masked) | Blocked
|  | Terraform - Infra Provisioning |  | Ansible Role | rpm |  | Transfer via data diode / air-gap media | Dev, Test, Prod |  |  |  | JFrog Access Token | N/A
|  | Terraform - Day-2 Configuration |  | Ansible Collection | ansible |  |  | All
|  | Platform Shared Service |  | Terraform Provider | terraform
|  |  |  | Terraform Module | generic
|  |  |  | VM / OS Image | pypi
|  |  |  | Generic Binary / Archive | maven
|  |  |  | GPG Key / Certificate | npm
Python Package
Maven / JAR
npm Package